Civil Engineering Division

Ref: CED/WO/1/2024-2025                                                                                     Date:22/08/2024

To,

M/SBansal and Company

1- Nehru Colony, Thatipur, Gwalior.

Dear Sirs,

Sub: Construction of Service Rack/ Bridge and Miscellaneous Civil & Electrical works for P-1185 structures at RR Site, Kota, Rajasthan

Ref.:1. Tender Notice No . BARC/CED/ET/2/2024-2025 Dated 15/05/2024

Test 123

1. We are pleased to accept on behalf of the President of India, your offer for the above work, amounting to (₹) 4,05,36,691.00

2. A copy of Schedule 'A' (Schedule of materials) and Schedule 'B' (Schedule of Quantities) incorporating the final accepted rates and quantities are enclosed

3. The work shall be carried out by you on the basis of the drawings, specifications, general directions and conditions, special conditions and additional conditions of contract etc

4. You are now requested to commence the work on or before 16/09/2024 . The entire work covered under the contract shall be completed by you within 10 calendar months (including monsoon period) with stipulated date of completion as 15/07/2025 . The entire work shall be carried out in accordance with the tender specifications, conditions of contract, as per working drawings, which will be issued to you in a phased manner as the work progresses

5. TRIPATHI AMIT KUMAR. SO/E will be in-charge of this work at the site under the control of NAIR D S, Project Engineer (M), under the overall control of MAHESH KUMAR S, Superintendent Engineer (S), and he may be contacted for all further instructions regarding this work.

6. As per conditions of contract, you are required to furnish a total Security Deposit amounting to (₹) 10,13,417.28. Security Deposit will be collected @ 2.5 % of the gross amount of your each running and final bill by deductions till the required amount of Security Deposit is recovered.

7. In addition, you are requested to deposit (₹) 12,16,100.73 towards Performance Security within  15,fifteen days from the date of issue of this letter in the form of fixed deposit receipts of Scheduled Bank or in the form of Government Securities. The Earnest Money Deposit submitted by you along with the tender will be returned to you after receipt of Performance Security Deposit subsequent to confirmation of Performance Security Deposit by Bank, in case Performance Security Deposit is in the BG form. The performance security can also be accepted in the form of Bank Guarantee from Scheduled / Nationalized Banks as per the proforma enclosed, in case where the value of Performance guarantee exceeds 1.0 lakh.

8. You are required to follow confidentiality clause as per enclosed Annexure 'A' and strictly comply with provisions under Contract Labour (Regulation and Abolition) Act 1970 as per enclosed Annexure 'B'.

9. A formal contract agreement for the work will be drawn up and you are required to sign the same on intimation, in the office of AAO, Civil Engineering Division, BARC. However, until a formal contract agreement is signed, the tender submitted by you, the letters referred to above and this letter of acceptance will form a binding contract between us

10. A phased programme for completion of the work keeping the ultimate time limit of within 10 calendar months including the monsoon period as agreed by you shall be drawn up and sent to us within 15 days from the date of issue of this communication. This programme after acceptance shall form a part of the contract for the purpose of clause 2, Section III of 'General conditions of contract'.

11. Income Tax @ 2 %, Surcharge, Primary Education Cess and Secondary and Higher Education Cess on Income Tax as applicable will be deducted from the payments made to you.

12. TDS-GST @ 18 % of gross value of work done will be deducted from the payments made to you.

13. Goods and Service Tax (GST) as applicable as per the extent order on the subject on the above work shall be paid by the contractor to concerned Department.

14. Labour welfare cess @ 1 % of gross value of work done will be deducted from the payments made to you.

15. Any other taxes/cess as per Government directives will be deducted from the payments made to you, from time to time.

16. The name of your authorized representative at the site to whom instructions can be issued may please be intimated.

17. You shall follow all safety rules and security procedures that are in vogue and applicable during the execution of work. You are requested to verify the character and antecedents of the labor employed by you through local address proof issued by competent authorities such as ration card, driving license, electricity bills, telephone bill, gas connection document, etc. The nationality of contract laborers also needs due verification.

18. The work shall be executed in accordance with the safety guidelines of 'Construction safety Manual for Works Contract (BARC/2011/E/006)' as given on the BARC website and other safety guidelines provided in the GCC and Special Instructions to the Tenderers to complete the work in a safe and incident-free manner. You will have to deploy Safety Officer(s) and Safety Steward(s) of required qualification and follow all safety procedures like work permits, height passes, job cards for excavations, checklists, etc., as per the above Construction safety Manual for Works Contract. In case the maximum worker strength is less or equal to 500, you shall identify a Site Engineer to perform the duty of the Safety Engineer/Officer at the site. NAIR D S is appointed as Safety Observer from CED, BARC, for the above work. Any person working or visiting the work site shall be provided with the required safety PPEs.

19. You are requested to obtain immediately Police Verification Reports of your regular staff deployed at the site in respect of this contract and same along with necessary application to allow them to enter BARC premises to carry out assigned work.

20. You are now requested to depute your authorized representative to this office who holds the power of attorney to sign the formal agreement within 15 days from the date  of receipt of this work order, with a prior appointment with AAO, Civil Engineering Division, BARC with a copy of power of attorney. Till formal agreement is signed, this work order together with the tender shall form a binding contract between us.

21. This Work order is issued in duplicate. You are requested to return the duplicate copy duly signed and stamped by you on each and every page as acknowledgment and confirmation of the acceptance of this work order within 7 days from the date of receipt of this work order.

Yours faithfully

,Chief Engineer,CED

Bhabha Atomic Research Centre

For & on behalf of the President of India

Encl: 1. Schedule 'A'

2. Schedule 'B' with accepted rates & quantities.

3. Annexure 'A'& 'B'

4. Appendix 'B'

CC.

1.Accounts Officer (W), BARC – along with copy of Schedule A & B

2.A.A.O,CED, BARC – Along with copy of Schedule A & B. The lowest offer of M/s. Bansal and Company has been accepted by the Competent Authority. The original Comparative Statements are enclosed.

The details of sanction are as under:

| F.S. No. | : | R&D-052-2019 - |
| --- | --- | --- |
| Head of Account | : | 540100401131072 Major Works |
| C.C. No. | : | 512772 DPR Sub-Project No. NA, Title: |
| T.S. No . | : | CED/CE/7/2024-2025 |

3. MAHESH KUMAR S, Superintendent Engineer (S) – along with a copy of Schedule A&B & CST.

4. NAIR D S , Project Engineer (M) - along with a copy of Schedule A&B & CST.

5. TRIPATHI AMIT KUMAR, along with a copy of Schedule A&B and CST. They are requested to follow the codal provision while executing the high-rated items. They are requested to maintain a register in the prescribed form for all items up-to-date quantities. Additional quantities will be dealt with as per clause 12 of GCC. For additional quantities up to 10% of agreement quantities, no approval is required. Beyond 10% and up to the deviation limit, in-principal approval is required before execution, and beyond the deviation limit, no quantity should be executed unless the market rate is approved by the competent Authority. They are also requested to maintain a hindrance register as per CPWD manual and to compile the agreement and put up the same to the Engineer In-Charge for forwarding to AAO,CEDfor finalizing the agreement.

6. NAIR D S, Safety Observer, CED

7. Dy. Establishment Officer, SR&W, BARC - for information (without enclosure).

| A | Stipulated date of commencement of work | : | 16/09/2024 |
| --- | --- | --- | --- |
| B | Stipulated date of completion of work | : | 15/07/2025 |
| C | Maximum Number of workers to be employed on any day | : |  |

8., along with copy of Schedule A&B and CST.

CC: SE(P) - for information please

CC: Chief Security Officer, BARC - for information please.

CC: Head, A&SED - for favor of information please.

CC: Head,CED&Engineering Service Group- for favor of information please

ANNEXURE 'A'

49: Confidentiality clause in contracts entered into by BARC

I. Confidentiality:

No party shall disclose any information to any third party concerning the matters under this contract generally. In particular, any information identified as 'Proprietary' in nature by the disclosing party shall be kept strictly confidential by the receiving party and shall not be disclosed to any third party without the prior written consent of the original disclosing party.

This clause shall apply to the sub-contractors, consultants, advisors, or the employees engaged by a party with equal force.

II. 'Restricted information' categories under Section 18 of the Atomic Energy Act, 1962, and 'Official Secrets' under Section 5 of the Official Secrets Act, 1923:-

Any contravention of the above-mentioned provisions by any contractor, subcontractor, consultant, adviser, or the employees of a contractor will invite penal consequences under the above said legislation.

III. Prohibition against the use of BARC's name without permission for publicity purposes:-

The contractor or sub-contractor, consultant, adviser, or the employees engaged by the contractor shall not use BARC's name for any publicity purpose through any public media like Press, Radio, TV, or Internet without the prior written approval of BARC.

-------------------------------------------

ANNEXURE 'B'

PROVISIONS UNDER CONTRACT LABOUR (REGULATION & ABOLITION)

ACT 1970 REQUIRED TO BE FULFILLED BY CONTRACTORS

1) Every Contractor employing 20 or more workmen on any day should obtain a license from Asst. Labour Commissioner, Sion, Mumbai. They should also obtain Registration under BOCW Act if they are engaged in construction activities. (Rule 12).

2) Every Civil Contractor employing 10 or more workmen should obtain Registration under Building and other Construction Workers Act from Asstt. Labour Commissioner, Sion, Mumbai.

3) Notice of commencement of contract work should be given to Labour Enforcement Officer by the Contractor in Form VI-A (Rule 81 (3)).

4) Notice of completion of contract work should be given to Labour Enforcement Officer by the Contractor in Form VI-A (Rule 81 (3)).

5) Notices showing rates of wages, hours of work, wage periods, date of payment of wages, date of payment of unpaid wages, names and addresses of inspections in English, Hindi and in the local language should be displayed at Work Site {Rule 81 (i)(i)}.

6) A copy of the above Notice is to be sent to Labour Enforcement Officer.

7) Maintain a Register of Workmen in Form XIII (Rule 74).

8) Issue Employment Card to Workmen in Form XIV (Rule 76).

9) Issue 6 Service Certificate to workmen in Form XV on termination of employment for any reason whatsoever (Rule 77).

10) Maintain Muster Roll of Workmen in Form XVI {Rule 78 (l) (a) (i)}.

11) Maintain Register of wages in Form XVII. Contractors may maintain a Combined Register of Wages-cum-Muster Roll, if the wage period is a fortnight or less.

12) Provide Wage slip to workmen in Form XIX {Rule 78 (l) (bl)}.

13) Maintain a Register of Deduction for Damage/Loss in Form XX {Rule 78 (l) (a) (ii)}.

14) Maintain a Register of Fines in Form XXI {Rule 78 (l) (a) (ii)}.

15) Maintain a Register of Advances in form XXll {Rule 78 (l)(a) (ii)}.

16) Maintain a Register of Over-time in Form XXll {Rule 78 (l)(a) (iii)}.

17) Send Half-Yearly Return in Form XXIV to ALC I LEO {Rule 82 (l)}.

18) A First Aid Box with essential medical items to be maintained (Rule 58).

19) Every contractor should ensure disbursement of wages to his workmen in the presence of the authorized representative of BARC (Rule 72).

20) Every Contractor shall display an abstract of the Act and Rules in English, Hindi and in the language spoken by the majority of the workers (Rule 79).

APPENDIX-'B'

FORM OF PERFORMANCE SECURITY BANK GUARANTEE BOND

In consideration of the President of India (hereinafter called 'The Government') having offered to accept the terms and conditions of the proposed agreement (Work Order No. ) between...................... and ...........................(hereinafter called 'the said contractor(s)').................... For the work.(hereinafter called 'the said agreement') having agreed to production of an irrevocable Bank Guarantee for ₹ ............................. (Rupees only) as security/guarantee from the contractor(s) for compliance with his obligations in accordance with the terms and conditions in the said agreement.

1) We (indicate the name of the bank) (hereinafter referred to as 'the Bank') hereby undertake to pay to the Government an amount not exceeding ₹. only) on demand by the Government.

2) We (indicate the name of the bank) do hereby undertake to pay the amounts due and payable under this Guarantee without any demur, merely on a demand from the Government stating that the amount claimed is required to meet the recoveries due or likely to be due from the said contractor(s). Any such demand made on the Bank shall be conclusive as regards the amount due and payable by the Bank under this Guarantee. However, our liability under this guarantee shall be restricted to an amount not exceeding ₹.................... (Rupees only).

3) We, the said bank further undertake to pay the Government any money so demanded notwithstanding any dispute or disputes raised by the Contractor(s) in any suit or proceeding pending before any court or Tribunal relating thereto, our liability under this present being absolute and unequivocal. The payment so made by us under this bond shall be a valid discharge of our liability for payment thereunder, and the contractor(s) shall have no claims against us for making such payment.

4) We................................... (Name of Bank). further agree that the Guarantee herein contained shall remain in full force and effect during the period that would be taken for the performance of the said agreement and that it shall continue to be enforceable till all the dues of the Government under or by virtue of the said agreement have been fully paid and its claims satisfied or discharged or till Engineer-in-Charge on behalf of the Government certifies that the terms and conditions of the said agreement have been fully and properly carried out by the said contractor(s) and accordingly discharges this Guarantee.

5) We................................... (Name of Bank). further agree with the Government that the Government shall have the fullest liberty without our consent and without affecting in any manner our obligations hereunder to vary any of the terms and conditions of the said agreement or to extend the time of performance by the said contractor(s) from time to time or to postpone for any time or from time to time any of the powers exercisable by the Government against the said contractor(s) and to forbear or enforce any of the terms and conditions relating to the said agreement, and we shall not be relieved from our liability by reason of any such variation, or extension being granted to the said contractor(s) or for any forbearance, act of omission on the part of the Government or any indulgence by the Government to the said contractor(s) or by any such matter or thing whatsoever which under the law relating to sureties would, but for this provision, have effect relieving us.

6) This Guarantee will not be discharged due to the change in the constitution of the Bank or the contractor(s).

7) We................................... (Name of Bank). lastly undertake not to revoke this Guarantee except with the previous consent of the Government in writing.

8) This Guarantee shall be valid up to unless extended on demand by the Government. Notwithstanding anything mentioned above, our liability against this guarantee is restricted to ₹...................... (Rupees only), and unless a claim in writing is lodged with us within six months of the date of expiry or the extended date of expiry of this guarantee, all our liabilities under this guarantee shall stand discharged.

Signed & Sealed

Dated the.................................... day of.................................... for. (Indicate the name of the Bank)

Government of India

Bhabha Atomic Research Centre

Civil Engineering Division

North Site, Trombay, Mumbai-400 085

SCHEDULE, - 'A' - SCHEDULE OF MATERIAL TO BE SUPPLIED BY THE DEPARTMENT

Name of Work : Construction of Service Rack/ Bridge and Miscellaneous Civil & Electrical works for P-1185 structures at RR Site, Kota, Rajasthan

Tender Notice No. : BARC/CED/ET/2/2024-2025

Schedule showing the materials to be supplied to the extent available by the Bhabha Atomic Research Centre for the work contracted to be executed & the rate at which recovery for such supply will be made from bills payable to Contractor.

| Sl.No. | Particulars | Rate at which the materials will be charged to contracted (issue rate & storage charges to be shown separately) |  |  | Place of Delivery |
| --- | --- | --- | --- | --- | --- |
|  |  | Approx. Qty. | Unit | Rate |  |
| 1 | Water charges | As Required | - | % of Gross value of Work Done - 1 | At one point near the site of work |
| 2 | Electrical Charges | As Required | - | Free of Cost | At one point near the site of work |

Notes:

1. The persons or firm submitting the tender should see that the rates in the above schedule are filled up by the Engineer on the issue of the form prior to the submission of the tender.

2. The material supplied by the Department at Departmental stores specified above shall be transported (including loading unloading) by the contractor at his own cost.

3. The contractor from open market at his own cost will procure all the materials, which are not included in the above schedule.

4. Contractor shall make required length of electrical cable, GI pipes, Hose pipes and water storing arrangements etc.

5. For stores supplied item, if lost or damaged while in charge and custody of the contractor, recovery shall be made by the Department at the rate specified in Proforma of Schedule A to F or the cost thereof + 1 % handling charges, whichever is higher. For the purpose of arriving at the cost of materials, rates at which the articles have been purchased by the Department or the ruling market rates, whichever is higher, shall be taken into consideration.

Government of India

Bhabha Atomic Research Centre

Civil Engineering Division

North Site, Trombay, Mumbai-400 085

Schedule 'B'- Schedule of Quantities (Price Bid)

Name of Work : Construction of Service Rack/ Bridge and Miscellaneous Civil & Electrical works for P-1185 structures at RR Site, Kota, Rajasthan

Tender Notice No. : BARC/CED/ET/2/2024-2025

| Sl.No. | Quantity | Description of Item | Unit | Rate ( ₹ ) |  | Amount ( ₹ ) |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | (In Fig) | (In words) |  |
| 1 |  | Section-A : Civil Works Earth work excavation by mechanical means (Hydraulic excavator) / manual means in all types of soil other than soft and hard rock, dressing the sides of foundation, ramming of bottom etc. including shoring and dewatering (if necessary) and refilling with selected excavated earth in layers of not more than 500 mm thick, each layer well rammed and consolidated including disposing the surplus earth within a distance of 200 m all as per specifications including clearing Jungle, uprooting of vegetation, grass, etc. complete and as directed by the Engineer-in-charge |  |  |  | 0.00 |
| 1.01 | 50 | From 0.00 to 1.50 m depth from Average Ground Level | CuM | 150 | one hundred fifty | 7,500.00 |
| 2 |  | Earth work excavation by mechanical means (Hydraulic excavator) / manual means in foundation, in Soft Rock including shoring, dewatering if necessary, dressing the sides, ramming the bottom, refilling the sides etc. with available selected excavated earth in layers of not exceeding 500 mm in depth, each layer well rammed and consolidated disposal of surplus excavated material within a lead of 200 m complete as per specifications and as directed by the Engineer-in-charge. |  |  |  | 0.00 |
| 2.01 | 70 | From 0.00 to 1.50 m depth from Average Ground Level | CuM | 150 | one hundred fifty | 10,500.00 |
| 3 |  | Earth work excavation in foundation in Hard Rock by Chiselling and / or by mechanical means (Hydraulic excavator) / Manual means including dewatering if necessary, dressing the sides, ramming the bottom, and stacking and / or disposing within a distance of 200 m and filling the sides of foundation with available selected excavated earth in layers not exceeding 500 mm in depth, each layer well rammed and consolidated etc.complete all as per specifications and as directed by the Engineer-in-Charge. |  |  |  | 0.00 |
| 3.01 | 120 | From 0.00 to 1.50 m depth from Average Ground Level | CuM | 500 | five hundred | 60,000.00 |
| 3.02 | 50 | From 1.50 to 3.00 m depth from Average Ground Level | CuM | 500 | five hundred | 25,000.00 |
| 4 |  | Earth work excavation in foundation in Hard Rock by controlled Blasting (including explosive,drilling, muffling, pre shear line drilling) and by mechanical means (Hydraulic excavator) / Manual means including dewatering if necessary, dressing the sides of foundation, ramming the bottom of foundation, stacking and / or disposing within a distance of 200 m and filling the sides of foundation with available excavated earth in layers not exceeding 250 mm in depth, each layer well rammed and consolidated etc. complete all as per specifications and as directed by the Engineer-in-Charge. Blasting works to be executed as per safety norms and as per specifications and as directed by the Engineer-in-charge. |  |  |  | 0.00 |
| 4.01 | 50 | From 0.00 to 1.50 m depth from Average Ground Level | CuM | 1000 | one thousand | 50,000.00 |
| 4.02 | 50 | From 1.50 to 3.00 m depth from Average Ground Level | CuM | 1000 | one thousand | 50,000.00 |
| 4.03 | 50 | From 3.00 to 4.50 m depth from Average Ground Level | CuM | 1200 | one thousand two hundred | 60,000.00 |
| 4.04 | 50 | From 4.50 to 6.00 m depth from Average Ground Level | CuM | 1500 | one thousand five hundred | 75,000.00 |
| 5 | 100 | Supplying and stacking good excavated earth available at site, including compaction of earthwork in embankment under optimum moisture conditions to give at least 95% of the maximum dry density ( Proctor density) | CuM | 250 | two hundred fifty | 25,000.00 |
| 6 |  | Lead charges for 1st 1 KM or part thereof, by mechanical transport including loading unloading, stacking / levelling etc. |  |  |  | 0.00 |
| 6.01 | 25 | Soil | CuM | 200 | two hundred | 5,000.00 |
| 6.02 | 220 | Rock | CuM | 200 | two hundred | 44,000.00 |
| 6.03 | 50 | Debris | CuM | 250 | two hundred fifty | 12,500.00 |
| 7 |  | Lead charges for Lead exceeding 1 KM but not exceeding 2 KM, by mechanical transport including loading, unloading, stacking / levelling etc. |  |  |  | 0.00 |
| 7.01 | 25 | Soil | CuM | 300 | three hundred | 7,500.00 |
| 7.02 | 220 | Rock | CuM | 300 | three hundred | 66,000.00 |
| 7.03 | 50 | Debris Note: The rates in respect of Item Nos. 6 and 7 are applicable for NET Quantities arrived at after making deduction for voids @ 20% in respect of soil ,@ 50% in respect of Rock and @30% in respect of debris from corresponding STACK / TRUCK Measurement. | CuM | 350 | three hundred fifty | 17,500.00 |
| 8 | 1500 | Supplying and injecting with approved quality chemical emulsion at the rates and concentrations as per IS 6313-2001 Part II for preconstructional antitermite treatment and creating a chemical barrier under and alround the masonry pits, masonry foundations, wall trenches, plinth filling, junctions of wall and floor, expansion joints, surfaces of RCC works for a depth of min. 500 mm from the finished ground level, surrounding of pipes, conduits etc., walls retaining soil above floor level, apron and drain along the perimeter of the building including all byeworks complete as per specification / IS 6313:2001 or latest revision and direction of Engineer Incharge (only ground floor plinth area of the building will be measured for the payment in the following three stages. i) 20% after completion of the foundations ii) 50% after completion of the ground floor flooring iii) 30% after completion of all treatment works including ground floor doors and windows. Work to be executed by approved agency and specified guarantee for 10 (ten) years shall be furnished by the contractor. | SqM | 90 | ninety | 1,35,000.00 |
| 9 | 50 | Providing and laying in position cement concrete of 1:4:8 (1 cement, 4 crushed sand, 8 graded stone aggregate of maximum size 20 / 40 mm) / M-7.5 grade with minimum cement content 170 Kg/m3 including consolidation, finishing, curing etc. complete as per specifications and drawings but excluding the cost of Form work shuttering, centering complete at all levels | CuM | 3500 | three thousand five hundred | 1,75,000.00 |
| 10 | 200 | Providing and laying in position cement concrete of 1:3:6 (1 cement, 3 crushed sand, 6 graded stone aggregate of maximum size 20 mm)/ M-10 grade with minimum cement content 220 Kg/m3 including consolidation, finishing, curing etc. complete as per specificationsand drawings but excluding the cost of Form work shuttering, centering complete at all levels | CuM | 5500 | five thousand five hundred | 11,00,000.00 |
| 11 | 150 | Providing and laying in position cement concrete of 1:2:4 (1 cement, 2 crushed sand, 4 graded stone aggregate of nominal size 20 mm)// M-15 grade with minimum cement content 320 Kg/m3 including consolidation, finishing, curing etc. complete as per specification and drawings but excluding the cost of Formwork shuttering, centering and steel reinforcement at all Levels | CuM | 5000 | five thousand | 7,50,000.00 |
| 12 | 200 | Providing and laying in position Reinforced Cement Concrete (RCC) of grade M-20 using 20 mm maximum size aggregates and crushed sand of approved quality including admixtures of approved brand and quality (plasticisers / super plasticisers), weigh batching, mechanical mixing, transporting, placing, vibrating, consolidation, finishing, curing etc. complete but excluding the cost of centering, shuttering and reinforcement complete as per specifications up to Plinth Level | CuM | 6000 | six thousand | 12,00,000.00 |
| 13 | 50 | Providing and laying in position Reinforced Cement Concrete (RCC) of grade M-20 using 20 mm maximum size aggregates and crushed sand of approved quality including admixtures of approved brand and quality (plasticisers / super plasticisers), weigh batching, mechanical mixing, transporting, placing, vibrating, consolidation, finishing, curing etc. complete but excluding the cost of centering, shuttering and reinforcement complete as per specifications in superstructure upto 20.00 m height | CuM | 7000 | seven thousand | 3,50,000.00 |
| 14 | 150 | Providing and laying in position Reinforced Cement Concrete (RCC) of grade M-30 using 20mm maximum size aggregates and crushed sand of approved quality including admixtures of approved brand and quality (plasticiser or super plasticiser) if required, including weigh batching, mechanical mixing, transporting, placing, vibrating, consolidation, finishing, curing etc. complete but excluding the cost of centering, shuttering and reinforcement complete as per specifications up to Plinth Level. | CuM | 8000 | eight thousand | 12,00,000.00 |
| 15 | 1000 | Providing and laying in position Reinforced Cement Concrete (RCC) of grade M-30 using 20mm maximum size aggregates and crushed sand of approved quality including admixtures of approved brand and quality (plasticiser or super plasticiser) if required, including weigh batching, mechanical mixing, transporting, placing, vibrating, consolidation, finishing, curing etc. complete but excluding the cost of centering, shuttering and reinforcement complete as per specifications in superstructure up to 20.00 m height . | CuM | 10000 | ten thousand | 1,00,00,000.00 |
| 16 | 1800 | EXTRA (over Item nos. 9,10,11,12, 13,14,15) for Ready Mixed Concrete of all Grades of RCC / PCC manufactured in Fully Automatic Batching plant produced inside Project areas as per direction of Engineer-in-charge complete as per specifications and as directed Note : Minimum cement contentfor item nos. 12, 13, 14 and 15 is as enclosed in the "Table for Minimum Cement Content". | CuM | 250 | two hundred fifty | 4,50,000.00 |
| 17 | 100 | Providing and laying in position PLUM Concrete with 70 % cement concrete of 1:3:6 (1 cement, 3 crushed sand, 6 graded stone aggregate of maximum size 20 mm) and 30 % 150 to 230 mm size soling stones spreading uniformly as per directions of the Engineer-in-Charge including consolidation, finishing, curing etc. complete as per specifications and drawings but excluding the cost of Form work shuttering, centering complete at all levels | CuM | 4000 | four thousand | 4,00,000.00 |
| 18 | 100 | Providing supplying and sealing the 50 mm wide Expansion Joints using Gun grade(GG) High performance, elastomeric polysulphide joint sealant suitable for RCC Construction Joints of approved make and satisfying the technical specifications as mentioned below and as per relevant codes and standards, by removing the expansion joint board up to 25 mm deep and cleaning the suface neatly and filling Gungrade sealent up to 25 mm deep to the lines and levels complete all as per manufacturers specifications and as directed by the Engineer-In-Charge. Note : 1. Tentative/suggested model and make of Gun grade(GG) High performance, elastomeric polysulphide joint sealant for guidance of bidder(s) : 'MASTERFLEX 700i' of M/s BASF or approved equivalent. 2. The technicalspecifications regarding Gun grade (GG) High performance,elastomeric polysulphide joint sealant suitable for RCCConstruction Joints is as enclosed in the "Table for Technicals pecifications of Gun grade (GG) High performance,elastomeric polysulphide joint sealant suitable for RCC Construction Joints". | M | 200 | two hundred | 20,000.00 |
| 19 | 100 | Providing and fixing in position 100 mm thick (adding and pasting 2 nos of 50 mm thick boards) cross-linked, pre-molded, high-performance compressible polymeric filler board in expansion joints to the required size and shape, placing and keeping in position complete as per specifications and drawings and as directed by the Engineer in charge. Note : 1. This item to be operated for Outer most Structural members or as directed by Engineer in Charge. 2. Tentative/suggested make for guidance of bidder(s) - M/s Supreme Duraboard or approved equivalent | SqM | 300 | three hundred | 30,000.00 |
| 20 | 1000 | Providing and fixing required width of anodized 6 mm thick Aluminium sheet covering over expansion joints with iron screws as per design to match the colour / shade of wall treatment including all materials, labour, scaffolding complete as per drawings and specifications. | Kg | 300 | three hundred | 3,00,000.00 |
| 21 | 190 | Providing Reinforcement Steel for reinforced cement concrete at all levels including supplying, preparation of bar bending schedules, cutting, bending, transporting, fixing, tieing in position with PVC coated G.I binding wire, all labour charges, cost of cover blocks in specified grade of concrete etc. complete as per specifications and drawings. Steel supplied by the contractor. Using TMT bars of Fe-500D grade of all sizes .TMT bars to be supplied by the contractor shall conform to IS – 1786 (Latest edition) and BARC specification Note: 1) The contractor shall supply documentary evidence of purchase of steel, Test certificate from approved manufacturers and also testing third party from approved laboratories without any extra cost. 2) Binding wire required for the work will have to be supplied by the contractor at their own cost and will not be measured for payment. 3) Cover blocks shall be of same grade of concrete. | MT | 80000 | eighty thousand | 1,52,00,000.00 |
| 22 | 8 | Providing Structural steel work in M.S Plain Plates and Chequrred Plates for Embedded Parts, Trench Covers, Connection plates etc.including cutting, hoisting, fixing in position and applying a priming coat of approved zinc chromate steel primer etc.including cost of structural steel Plates, welding all labour charges etc. complete as per drawings and specifications. Using materials of approved manufacturers. All test reports to be provided along with the supply of the materials conforming to IS:2062 | MT | 90000 | ninety thousand | 7,20,000.00 |
| 23 |  | Providing Structural steel work using angles, channels, joists and other sections, welded and / or bolted in built up sections for trusses , structural steel floors, frame works, monorails and other structures including supplying, cutting, welding, fabricating, hoisting, fixing in position, applying a priming coat of approved steel primer etc. complete all as per specifications, drawings and as directed by the Engineer in charge |  |  |  | 0.00 |
| 23.01 | 6 | Up to and including 300 mm Joists, 350 mm channels, and below sections using materials of approved manufacturers. (ISI marked) All test reports to be provided along with the supply of the materials conforming to IS:2062 | MT | 100000 | one lakh | 6,00,000.00 |
| 23.02 | 3 | Above 300 mm Joists, 350 mm channels, sections using materials of approved manufacturers. (ISI marked) All test reports to be provided along with the supply of the materials conforming to IS:2062 Notes for Item No. 22, 23.01 and 23.02 : 1. The contractor shall supply documentary evidence of purchase of steel, Test certificate from approved manufacturers and also third party testing from approved laboratories with out any extra cost. 2. Welding weights, connections, bolts and nuts shall not be measured for payment but the cost of which shall be deemed to have been included in the rates. 3. Welding Electrodes from approved manufactrers meeting all the technical specifications (the electrode gives smooth radiographic quality weld with low spatter and smoke) grade only shall be used. 4. Holes to be drilled only by Drilling machines and gas cutting of holes are not permitted. 5. Rate inclusive of all consumables like GAS, welding electrodes and tools and tackles etc. | MT | 100000 | one lakh | 3,00,000.00 |
| 24 | 12 | Providing, supplying, cutting, welding, fabricating, hoisting and fixing in position structural steel members like pergolas, trusses, purlins, posts etc. using MS hollow / circular / square / rectangular tubular sections including applying a coat of Zinc chromate primer of approved make all as per specifications as per relevent codes and standards; all as per specifications, drwaings and as dircted by Engineer in Charge Note: 1. Yst 310 Conforming to IS 4923:1997 (Reaffirmed in 2009) with yield stregth of 310 N/mm2 (For all rectangular Box sections Grade of steel to be used.) 2. Structural steel confirming to IS 2062 shall be supplied from approved manufacturers from their own plants rolled from virgin materials to be procured directly or from their authorised dealers and test certificate to be produced. 3. The contractor shall supply documentary evidence of purchase of steel, Test certificate from approved manufacturers and also third party testing from approved laboratories with out any extra cost. 4. Welding weights, connections, bolts and nuts shall not be measured for payment but the cost of which shall be deemed to have been included in the rates. 5. Welding Electrodes from approved manufactrers meetinf all the technical specifications (the electrode gives smooth radiographic quality weld with low spatter and smoke) grade only shall be used. 6. Holes to be drilled only by Drilling machines. Gas cutting of holes are not permitted . 7. Rate inclusive of all consumables like Gas, welding electrodes and tools and tackles etc. | MT | 100000 | one lakh | 12,00,000.00 |
| 25 | 300 | Providing and fixing hand rail of approved size by welding etc. to steel ladder railing, balcony railing and staircases railing including applying a priming coat of zinc chromate steel primer etc. complete as per specifications using M.S tubes of ISI marked (Medium) of specified diameter and thickness | Kg | 100 | one hundred | 30,000.00 |
| 26 | 150 | Providing and fixing hand rail using 304 grade Stainless Steel pipes of approved size and make or approved equivalent meeting all the technical specifications as per relevant codes and standards and quality by welding, mirror / matt polishing, fixing at site etc. for balcony railing and staircases railing including special sections as per drawings, specifications. complete as directed by the Engineer-in-charge | Kg | 350 | three hundred fifty | 52,500.00 |
| 27 | 600 | Providing and fixing 304 grade Stainless Steel pipes of approved size and make or approved equivalent meeting all the technical specifications as per relevant codes and standards and quality by cutting and placing in position including embedding if necessary complete as per specification and as directed by the Engineer in charge | Kg | 350 | three hundred fifty | 2,10,000.00 |
| 28 | 200 | Providing and fixing hand rail using Galvanized Iron Steel pipes of ISI Marked of approved size and make or approved equivalent meeting all the technical specifications as per relevant codes and standards as well as quality by welding etc. to steel ladder railing, balcony railing and staircases railing including applying a priming coat of approved steel primer etc. complete as per specifications | Kg | 350 | three hundred fifty | 70,000.00 |
| 29 | 50 | Providing and fixing in position 50 mm thick Thermocole board heavy density minimum 18.00 Kg/ Cu.m weight Wrapped in 200 micron thickness Polythene sheets and placing in machine foundation works complete as per specifications and drawings and as directed by the Engineer incharge. | SqM | 800 | eight hundred | 40,000.00 |
| 30 | 750 | Providing and fixing at all levels MS bolts including nuts and washers of approved size, quality and make or approved equivalent meeting all the technical specifications as per relevant codes and standards as per requirements, drawings complete all as directed at site by the Engineer in charge | Kg | 100 | one hundred | 75,000.00 |
| 31 | 50 | Providing and fixing at all levels SS bolts including nuts and washers of approved size, quality and make or approved equivalent meeting all the technical specifications as per relevant codes and standards as per requirements and as per specifications, drawings complete all as directed at site by the Engineer in charge | Kg | 120 | one hundred twenty | 6,000.00 |
| 32 | 150 | Providing and fixing fabricated embedded parts/ plates made 304 grade Stainless Steel pipes/ Plates/ Flanges etc. as per drawings of approved make or approved equivalent meeting all the technical specifications as per relevant codes and standards as well as quality by welding, fixing, embedding in concrete at site etc. as per drawings, specifications . complete. A sample to be fabricated and to be got approved by the Project Engineer before starting of work at site. This work to be executed through approved specialized agency. | Kg | 350 | three hundred fifty | 52,500.00 |
| 33 |  | Labour charges for Fixing in position in RCC / Masonary/ Form work Mild steel or Stainless steel fabricated Embedded Parts supplied by the Department including transporting from the departmental stores, aligning, fixing in position, welding, providing necessary supporting arrangements etc. complete all as per drawings and specifications and as directed by the Project Engineer. |  |  |  | 0.00 |
| 33.01 | 6000 | Weighing Up to 100 kg | Kg | 50 | fifty | 3,00,000.00 |
| 33.02 | 1000 | Weighing Up to 100 kg and inclusive of 1000 Kg | Kg | 75 | seventy-five | 75,000.00 |
| 33.03 | 1000 | Weighing above 1000 Kg Note : M.S. Steel / Reinforcement steel / jigs and fixtures if required for supporting shall be paid under relevant item. | Kg | 100 | one hundred | 1,00,000.00 |
| 34 |  | Providing , centering ,shuttering Form work using PVC film faced plywood to get a neat form finish surface for all types of structures including necessary strutting, proping, staging, supports etc and deshuttering the same after the specified time all as per drawings, specifications and as directed by the Engineer-in-charge at all levels |  |  |  | 0.00 |
| 34.01 | 1000 | For Sub Structure | SqM | 500 | five hundred | 5,00,000.00 |
| 34.02 | 4000 | For Super Structure | SqM | 800 | eight hundred | 32,00,000.00 |
| 35 | 1000 | Murum filling under floors of specified thickness in layers of not more than 150 mm thickness including supplying required materials and consolidation etc. complete (Murrum to be brought from out side campus of BARC) | CuM | 500 | five hundred | 5,00,000.00 |
| 36 | 1200 | Providing and fixing double tubular scaffolding system using H- frames with cup lock type on the exterior side upto seven story height made with 40 mm dia M.S. tube 1.5 m centre to centre horizontal and vertical tubes joining with cup and lock system with M.S. tubes, M.S. tube challies, M.S clamps and M.S staircase system in the scaffolding for working platform etc. and maintaining it in a serviceable condition for the required duration as approved and removing it thereafter. The scaffolding system shall be stiffened with bracings, runners, connection with building etc. wherever required for inspection of work at required locations with essential safety features for the workmen etc. complete as per directions and as approved by the Engineer -in - charge. The elevational area of the scaffolding shall be measured for payment purposes. The payment shall be made once irrespective of duration of scaffolding. | SqM | 500 | five hundred | 6,00,000.00 |
| 37 |  | Providing and Fixing Anchor Fastner of approved make meeting all the technical specifications as per relevant codes and standards including drilling in concrete as per requirement for fixing E.P.'s or other structures all as specified by the manufacturer complete all as per specifications and drawings. |  |  |  | 0.00 |
| 37.01 | 15 | 16 mm diameter 75 mm Long | Nos | 100 | one hundred | 1,500.00 |
| 37.02 | 15 | 16 mm diameter 100 mm Long | Nos | 100 | one hundred | 1,500.00 |
| 37.03 | 15 | 16 mm diameter 150 mm Long | Nos | 150 | one hundred fifty | 2,250.00 |
| 37.04 | 15 | 16 mm diameter 200 mm Long | Nos | 150 | one hundred fifty | 2,250.00 |
| 37.05 | 15 | 20 mm diameter 100 mm Long | Nos | 150 | one hundred fifty | 2,250.00 |
| 38 |  | Providing and fixing Mechanical Splicing of approved manufacturer meeting all the technical specifications as per relevant codes and standards using threaded coupler of all types to the reinforcement bars of specified dia and grade using high yield strength standard couplers of specially produced steel to join ribbed bearing bars machine cut end to end. Cost to include necessary supply of threaded couplers of various diametres , transportation, coupling at site by mechanical means , erection at site, testing of random samples, testing at site, protection of threaded ends using PVC covers, threading of rebars etc. complete. Cost to include necessary testing of joints ( 0.5% of the total joints) at site for tensile strength and as required by Engineer-in- Charge. Cost quoted shall include all materials and labour. Note : Tentative/suggested make of Mechanical Splicing for guidance of bidder(s) : M/s Dextra or approved equivalent |  |  |  | 0.00 |
| 38.01 | 10 | 16 mm dia | Nos | 100 | one hundred | 1,000.00 |
| 38.02 | 10 | 20 mm dia | Nos | 200 | two hundred | 2,000.00 |
| 38.03 | 10 | 25 mm dia | Nos | 300 | three hundred | 3,000.00 |
| 39 | 250 | Providing and Painting two coats of synthetic enamel paint on steel surfaces of approved brand and manufacture to give an even shade over a primer coat.including preparation of the surfaces, scaffolding complete. as per specifications and as directed by the Engineer-in-charge | SqM | 150 | one hundred fifty | 37,500.00 |
| 40 | 7000 | Section-B : Electrical Works Conduiting work 25mm FRLS PVC as per TSS-01 | M | 100 | one hundred | 7,00,000.00 |
| 41 | 100 | Conduiting work 32mm FRLS PVC as per TSS-02 | M | 100 | one hundred | 10,000.00 |
| 42 | 100 | Modular switch box (without cover plate and swithches) metallic on walls as per TSS-03 | Kg | 400 | four hundred | 40,000.00 |
| 43 | 100 | 40 mm (NB) GI pipe as per TSS-04 | M | 100 | one hundred | 10,000.00 |
| 44 | 300 | Sheet Steel MS Boxes as per TSS-05 | Kg | 300 | three hundred | 90,000.00 |
|  |  | TOTAL AMOUNT ( ₹ ) |  |  |  | 4,13,59,750.00 |
|  |  | Less(-) / Excess(+) % (IF ANY) |  | 1.99 |  | 8,23,059.03 |
|  |  | GRAND TOTAL ( ₹ ) |  |  |  | 4,05,36,690.97 |

IMPORTANT NOTICE

1.Police verification Certificate issued by Special Branch of Police is required for Contractor, Engineers, Supervisors and all the labour to work inside BARC and the same shall be arranged by the Contrator.